## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Environment setup | MUST HAVE | None | Shubham | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Implementation of dashboard UI layout | MUST HAVE | Environment setup | Shubham | 3- Completed
Sprint 1 | Sprint 1 | US- 03 | Implementation of transaction monitoring table | MUST HAVE | Sample dataset | Ishwar | 3- Completed
Sprint 2 | Sprint 2 | US- 04 | Implementation of search functionality for transactions | MUST HAVE | Transaction table UI | Ishwar | 3- Completed
Sprint 2 | Sprint 2 | US- 05 | Implementation of rule-based fraud detection | MUST HAVE | Transaction data | Ishwar | 3- Completed
Sprint 2 | Sprint 2 | US- 06 | Implementation of machine learning model for fraud detection | MUST HAVE | Dataset for training | Vidhya | 3- Completed
Sprint 3 | Sprint 3 | US- 07 | Integration of ML model with backend API | MUST HAVE | ML model + Backend setup | Vidhya | 3- Completed
Sprint 3 | Sprint 3 | US- 08 | Implementation of fraud alerts interface | SHOULD HAVE | Fraud detection logic | Srivalli | 3- Completed
Sprint 3 | Sprint 3 | US- 09 | Implementation of transaction generator for simulator | SHOULD HAVE | Data generation logic | Srivalli | 3- Completed
Sprint 3 | Sprint 3 | US- 10 | Integration of frontend with backend API's | MUST HAVE | Backend APIs | Shubham | 3- Completed
Sprint 4 | Sprint 4 | US- 11 | Implementation of fraud prediction input form | MUST HAVE | ML API | Arjun | 3- Completed
Sprint 4 | Sprint 4 | US- 12 | Implementation of analytics charts and visualization | COULD HAVE | Chart library(Chart.js) | Arjun | 3- Completed
Sprint 4 | Sprint 4 | US- 13 | Testing and validation of fraud detection system | MUST HAVE | Complete system integration | Shubham | 3- Completed
Sprint 4 | Sprint 4 | US- 14 | Final integration and debugging of complete system | MUST HAVE | All modules | Shubham | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 993 | 58 | 90 | 78 | 64 | 80 | 64 | 70 | 51 | 68 | 76 | 70 | 55 | 45 | 166
SPRINT 1 BACKLOG
US-01 | T1 | Install Node.js and React setup | 2026-02-03 | 2026-02-03 | Shubham | Project Setup | Completed | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T2 | Setup project folder structure | 2026-02-03 | 2026-02-03 | Shubham | Configuration | Completed | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T3 | Design dashboard layout(basic UI) | 2026-02-04 | 2026-02-04 | Shubham | UI Development | Completed | 4 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T4 | Crete sidebar navigation | 2026-02-04 | 2026-02-04 | Shubham | UI Development | Completed | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T5 | Create dashboard cards (Total, Fraud, Safe) | 2026-02-05 | 2026-02-05 | Shubham | UI components | Completed | 4 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T6 | Create transactions page UI | 2026-02-05 | 2026-02-05 | Ishwar | UI Development | Completed | 3 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T7 | Display transactions in table format | 2026-02-06 | 2026-02-06 | Ishwar | Data Rendering | Completed | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T8 | Implement search functionality | 2026-02-07 | 2026-02-07 | Ishwar | Feature Dev | Completed | 4 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T9 | Add sample transaction data(JSON) | 2026-02-07 | 2026-02-07 | Ishwar | Data Setup | Completed | 3 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T10 | Integrate chart(Bar graph) in dashboard | 2026-02-08 | 2026-02-08 | Ishwar | Visualization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T11 | Style UI using CSS(colors, layout) | 2026-02-08 | 2026-02-08 | Vidhya | UI Enhancement | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T12 | Create fraud alerts UI page | 2026-02-09 | 2026-02-09 | Vidhya | UI Feature | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T13 | Highlight fraud transactions in red | 2026-02-09 | 2026-02-09 | Vidhya | UI Logic | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T14 | Setup Axios for API calls | 2026-02-10 | 2026-02-10 | Vidhya | API Setup | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0
US-10 | T15 | Connect frontend with dummy backend | 2026-02-10 | 2026-02-10 | Vidhya | Integration | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0
US-11 | T16 | Create fraud prediction input form UI | 2026-02-11 | 2026-02-11 | Srivalli | UI Feature | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-12 | T17 | Improve chart visualisation(labels/colors) | 2026-02-12 | 2026-02-12 | Srivalli | Visualization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
US-13 | T18 | Test UI functionality | 2026-02-13 | 2026-02-13 | Srivalli | Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
US-13 | T19 | Fix UI bugs and errors | 2026-02-14 | 2026-02-14 | Arjun | Debugging | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-14 | T20 | Final UI integration and cleanup | 2026-02-15 | 2026-02-15 | Shubham | Finalization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 462 | 25 | 38 | 32 | 30 | 33 | 25 | 31 | 24 | 27 | 36 | 33 | 26 | 21 | 81
SPRINT 2 BACKLOG
US-05 | T21 | Setup Spring Boot project | 2026-02-16 | 2026-02-16 | Shubham | Backend Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T22 | Create project structure | 2026-02-16 | 2026-02-17 | Shubham | Backend Setup | Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T23 | Create Transaction model | 2026-02-17 | 2026-02-17 | Shubham | Backend Dev | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T24 | Implement rule-based fraud logic | 2026-02-18 | 2026-02-19 | Shubham | Logic Development | Completed | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T25 | Create REST API | 2026-02-19 | 2026-02-20 | Shubham | API Development | Completed | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T26 | Load dataset | 2026-02-16 | 2026-02-17 | Ishwar | Data Preparation | Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T27 | Data preprocessing | 2026-02-17 | 2026-02-18 | Ishwar | Data Processing | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T28 | Train ML model | 2026-02-18 | 2026-02-20 | Ishwar | Model Training | Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T29 | Handle imbalance | 2026-02-20 | 2026-02-21 | Ishwar | Model Improvement | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T30 | Evaluate model | 2026-02-21 | 2026-02-21 | Ishwar | Model Evaluation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T31 | Save model | 2026-02-21 | 2026-02-21 | Ishwar | Model Export | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T32 | Create ML API | 2026-02-22 | 2026-02-23 | Ishwar | API Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T33 | Test ML API | 2026-02-23 | 2026-02-23 | Ishwar | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T34 | Integrate ML with backend | 2026-02-24 | 2026-02-25 | Shubham | Integration | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-10 | T35 | Create transaction API | 2026-02-25 | 2026-02-26 | Vidhya | API Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-10 | T36 | Dashboard API | 2026-02-26 | 2026-02-26 | Srivalli | Backend Dev | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-10 | T37 | Enable CORS | 2026-02-26 | 2026-02-27 | Vidhya | Configuration | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US-07 | T38 | Test backend workflow | 2026-02-27 | 2026-02-28 | Shubham | Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-13 | T39 | Debug issues | 2026-02-28 | 2026-02-28 | Shubham | Debugging | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 198 | 11 | 16 | 13 | 11 | 13 | 8 | 13 | 11 | 11 | 16 | 15 | 12 | 9 | 39
SPRINT 3 BACKLOG
US-01
US-01 | T41 | Connect React UI with backend APIs | 2026-03-01 | 2026-03-02 | Shubham | Integration | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T42 | Fetch transaction data from backend | 2026-03-02 | 2026-03-03 | Shubham | Frontend Integration | Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T43 | Display backend data in UI table | 2026-03-03 | 2026-03-03 | Shubham | UI Update | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T44 | Connect fraud prediction form to API | 2026-03-04 | 2026-03-05 | Ishwar | Integration | Completed | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T45 | Display fraud prediction result in UI | 2026-03-05 | 2026-03-05 | Ishwar | UI Feature | Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T46 | Connect fraud alerts with backend data | 2026-03-06 | 2026-03-07 | Ishwar | Integration | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T47 | Display real-time fraud alerts | 2026-03-07 | 2026-03-07 | Ishwar | UI Feature | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T48 | Integrate transaction generator with system | 2026-03-08 | 2026-03-09 | Vidhya | Simulation | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US-02 | T49 | Test simulation data with fraud detection | 2026-03-09 | 2026-03-09 | Shubham | Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US-02 | T50 | Connect dashboard with backend stats API | 2026-03-10 | 2026-03-10 | Shubham | Integration | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-08 | T51 | Update charts with real-time data | 2026-03-10 | 2026-03-11 | Shubham | Visualization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
US-08 | T52 | Improve UI responsiveness and layout | 2026-03-11 | 2026-03-11 | Srivalli | UI Enhancement | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-10 | T53 | End-to-end system testing | 2026-03-12 | 2026-03-12 | Arjun | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
US-10 | T54 | Fix bugs and integration issues | 2026-03-12 | 2026-03-13 | Arjun | Debugging | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
US-11 | T55 | Performance testing with large dataset | 2026-03-13 | 2026-03-13 | Arjun | Performance Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-12 | T56 | Final system integration check | 2026-03-14 | 2026-03-14 | All Members | Finalization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
US-13 | T57 | Prepare project documentation | 2026-03-14 | 2026-03-14 | Vidhya | Documentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-13 | T58 | Prepare presentation (PPT) | 2026-03-14 | 2026-03-14 | Srivalli | Presentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-14 | T59 | Demo preparation and rehearsal | 2026-03-14 | 2026-03-14 | All Members | Demo Prep | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 4 | 6 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 5 | 3 | 2 | 13
SPRINT 4 BACKLOG
US-01 | T60 | Prepare backend for deployment | 2026-03-15 | 2026-03-16 | Shubham | Deployment Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T61 | Prepare frontend build (React build) | 2026-03-15 | 2026-03-16 | Shubham | Frontend Deployment | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T62 | Deploy ML model API on server | 2026-03-16 | 2026-03-17 | Shubham | ML Deployment | Completed | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T63 | Connect deployed backend with ML API | 2026-03-17 | 2026-03-18 | Shubham | Integration | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T64 | Deploy Spring Boot backend (local/server) | 2026-03-18 | 2026-03-19 | Shubham | Backend Deployment | Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T65 | Host frontend application | 2026-03-19 | 2026-03-20 | Shubham | Frontend Deployment | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T66 | Test full system in deployed environment | 2026-03-20 | 2026-03-21 | Ishwar | System Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T67 | Fix deployment-related issues | 2026-03-21 | 2026-03-22 | Ishwar | Debugging | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T68 | Improve UI design (final styling) | 2026-03-22 | 2026-03-23 | Vidhya | UI Enhancement | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-02 | T69 | Optimize backend performance | 2026-03-23 | 2026-03-24 | Vidhya | Performance Optimization | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
US-08 | T70 | Optimize ML model prediction speed | 2026-03-24 | 2026-03-24 | Srivalli | Model Optimization | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-08 | T71 | Security improvements (basic validation) | 2026-03-25 | 2026-03-25 | Srivalli | Security | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-10 | T72 | Prepare final dataset for demo | 2026-03-25 | 2026-03-26 | Srivalli | Data Preparation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
US-10 | T73 | Create final system screenshots | 2026-03-26 | 2026-03-26 | Arjun | Documentation | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US-11 | T74 | Update project documentation (report) | 2026-03-26 | 2026-03-27 | Arjun | Documentation | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
US-12 | T75 | Prepare final PPT slides | 2026-03-27 | 2026-03-27 | Vidhya | Presentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-13 | T76 | Practice final demo | 2026-03-27 | 2026-03-28 | All Members | Demo Prep | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-13 | T77 | Final system validation | 2026-03-28 | 2026-03-28 | All Members | Finalization | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-14 | T78 | Project submission and review | 2026-03-28 | 2026-03-28 | All Members | Submission | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on D29: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E29: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I30: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J30: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K30: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L30: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M30: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N30: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O30: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P30: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q30: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R30: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S30: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T30: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U30: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V30: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W30: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on D56: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E56: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I57: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J57: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K57: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L57: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M57: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N57: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O57: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P57: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q57: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R57: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S57: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T57: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U57: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V57: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W57: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on D84: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E84: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I85: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J85: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K85: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L85: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M85: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N85: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O85: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P85: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q85: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R85: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S85: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T85: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U85: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V85: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W85: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial project setup confusion | Resolved by team discussion and setup guide
Sprint 1 | Day 3 | UI alignment issues | Fixed using CSS adjustments
Sprint 1 | Day 5 | Chart integration error | Reinstalled chart library and corrected config
Sprint 1 | Day 7 | Data not displaying in table | Debugged state handling in React
Sprint 1 | Day 10 | Navigation routing issue | Fixed routes using React Router
Sprint 1 | Day 12 | Inconsistent UI styling | Standardized CSS across components
Sprint 1 | Day 14 | Minor UI bugs | Fixed before sprint completion
Sprint 2 | Day 2 | Spring Boot setup errors | Resolved dependency issues in pom.xml
Sprint 2 | Day 4 | API not returning data | Debugged controller and service layer
Sprint 2 | Day 6 | ML dataset imbalance | Handled using class weighting
Sprint 2 | Day 8 | Model accuracy issues | Tuned hyperparameters
Sprint 2 | Day 10 | CORS error between frontend & backend | Enabled CORS in backend
Sprint 2 | Day 12 | API integration delay | Coordinated between ML and backend team
Sprint 2 | Day 14 | Model integration bugs | Fixed API response handling
Sprint 3 | Day 2 | Frontend not connecting to backend | Corrected API URL and ports
Sprint 3 | Day 4 | Incorrect prediction output | Fixed feature mismatch issue
Sprint 3 | Day 6 | Fraud alerts not updating | Debugged state refresh logic
Sprint 3 | Day 8 | Simulation data inconsistency | Improved data generator logic
Sprint 3 | Day 10 | Chart not updating dynamically | Fixed state binding
Sprint 3 | Day 12 | System integration bugs | Performed end-to-end debugging
Sprint 3 | Day 14 | UI lag with large data | Optimized rendering
Sprint 4 | Day 2 | Deployment configuration issues | Fixed environment variables
Sprint 4 | Day 4 | Backend not accessible after deployment | Updated server port and endpoints
Sprint 4 | Day 6 | ML API latency | Optimized model loading
Sprint 4 | Day 8 | UI not loading properly on server | Fixed build and hosting issues
Sprint 4 | Day 10 | Performance issues under load | Optimized API responses
Sprint 4 | Day 12 | Documentation incomplete | Updated all project docs
Sprint 4 | Day 14 | Final demo issues | Prepared backup demo and fixed bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-01 | 2026-03-14 | Shubham | Improve UI consistency | Last-minute UI changes | Collaborating with team | Planned UI before implementation
2 | Sprint 1 | 2026-03-01 | 2026-03-14 | Ishwar | Better component reuse | Ignoring minor bugs early | Writing clean code | Added early bug tracking
3 | Sprint 1 | 2026-03-01 | 2026-03-14 | Arjun | Organized testing approach | Delaying testing | Regular testing | Created test checklist
4 | Sprint 2 | 2026-02-16 | 29-02-2026 | Vidhya | Proper API structuring | Hardcoding values | Code modularization | Followed MVC pattern strictly
5 | Sprint 2 | 2026-02-16 | 29-02-2026 | Srivalli | Better data preprocessing | Ignoring imbalance early | Model tuning | Applied class weighting
6 | Sprint 2 | 2026-02-16 | 29-02-2026 | Arjun | Document issues clearly | Untracked backend errors | Debugging systematically | Maintained issue logs
7 | Sprint 3 | 2026-03-01 | 2026-03-14 | Shubham | Enhance UI responsiveness | Overloading UI components | Improving UI design | Optimized layouts
8 | Sprint 3 | 2026-03-01 | 2026-03-14 | Ishwar | Better API handling | Ignoring API errors early | Frontend-backend sync | Added error handling
9 | Sprint 3 | 2026-03-01 | 2026-03-14 | Arjun | End-to-end testing | Late bug fixing | Testing regularly | Implemented integration testing
10 | Sprint 4 | 2026-03-15 | 2026-03-28 | Ishwar | Optimize backend performance | Unoptimized queries | Improving backend logic | Refactored APIs
11 | Sprint 4 | 2026-03-15 | 2026-03-28 | Shubham | Improve model efficiency | Overfitting issues | Model monitoring | Tuned model parameters
12 | Sprint 4 | 2026-03-15 | 2026-03-28 | Srivalli | Improve UI polish | Rushed styling | UI consistency | Applied final styling fixes